## Sheet1
# | Requirement | Dev Hours | Price $ per hour | DEV P | Total for the Item
1 | Remove the Dashboard from the app all together | 6 | 65 | 30
2 | Remove the Task Dashboard from the Bottom of the Screen | 3 | 65 | 30
3 | ON Client Module: |  | 65
3.1 | Change the amount of Seen records to: 50-100-150-200-250 | 2 | 65 | 30
3.2 | Remove Invoices as a tab | 3 | 65 | 30
3.2.1 | Remove Leads TAB | 4 | 65 | 30
3.2.2 | ADD a Notes Tab | 4 | 65 | 30
3.2.2.1 | Notes must be initially transferred from the LEADS MODULE/SECTION | 24 | 65 | 30
3.2.2.2 | User must be able to add additional notes as needed | 24 | 65 | 30
3.3 | remove edit and delete from the GRID and put them in the actual CLIENT Profile PAGE | 24 | 65 | 30
3.3.1 | Must have the ability to provide User of the system with the permission fro this function | 16 | 65 | 30
3.4 | ADD BANK INFORMATION TAB | 3 | 65 | 30
3.4.1 | Must have the ability to: 1. EDIT 2. ADD 3. DELETE (this must be Permission Based functionality) | 24 | 65 | 30
3.4.2 | Must add Client BANK INFO to the CREATE CLIENT Page as well | 8 | 65 | 30
3.4.3 | The Following DATA Sets for Banking to be added: 1. Bank Name 2. Billing State 3. Billing City 4. Billing ZipCode 5. Bank Account # 6. Bank Routing # | 16 | 65 | 30
3.5 | The User must have an ability to move back to previous screen or back without pressing the BACK button on the Web Browser | 24 | 65 | 30
3.6 | CLIENT ID# must be generated automatically and not manually | 2 | 65 | 30
4 | REMOVE TASKS TAB/MODULE from the LEFT SIDE MENU PANEL | 3 | 65 | 30
5 | REMOVE the DASHBOARD from the LEFT SIDE MENU PANEL | 3 | 65 | 30
6 | LEADS |  | 65 | 30
6.1 | must redo the basic info for potential clients (TBD) (This will be an approximate addition of 10-12 fields that must later on carry over to the Actual Client Setup/creration when converted) | more info needed | 65
6.2 | User must have an ability (button) to transfer over a lead to an actual CLIENT and finish out the required fields) | 24 | 65 | 30
7 | DEBT Process and System Flows: |  | 65 | 30
7.1 | In a case of starting from a DEBT Calculator, the User must be able to Create the Fiscal Calculations and then create a client | 16 | 65 | 30
7.2 | In a case of starting from a Lead section, the User must first move over the LEAD to the CLIENT and then create a new DEBT/CALCULATION | 24 | 65 | 30
7.3 | In a case of creating or generation a new DEBT/CALCULATION from an actual existing client the USER must go to the DEBT TAB | 16 | 65 | 30
7.4 | Once a USER Calculates a new DEBT and hits SAVE the data must be saved and the debt must be stored in the CLIENTS Profile | 14 | 65 | 30
7.4.1 | The User must be able to create a Contract from the DEBT/Calculation Created | 32 | 65 | 30
7.4.2 | The System MUST be able to STORE multiple DEBTs within the CLIENTS PROFILE | 16 | 65 | 30
7.4.3 | The data from the Calculator must be accurate and be transferred axactly as in the system to the CONTRACT | 16 | 65 | 30
7.4.4 | The USER MUST NOT be able to EDIT the contract in Adobe Esign. Any Changes that need to be made must be made within the system and exported to Adobe Esign | 24 | 65 | 30
7.4.5 | The Payment breakdown is currently not working correctly as far as the Amount of payments calculated in the system | 16 | 65 | 30
8 | Need to Remove the DEPARTMENTS from the LEFT Side Menu | 3 | 65 | 30
9 | Need to Modify Settings Section/Module 1. need to have a Create USER 2. EDIT User | 24 | 65 | 30
9.1 | additional functionality will be scoped out Need to provide a swag for a descent Robust functionality |  | 65
10 | Systems Historical Capability for User Modifications (Nice to Have) | need more time for research | 65